## Slide 1
eMS Reporting
Silistra, 26.10.2018
Drobeta Turnu Severin, 30.10.2018

## Slide 2
REPORTING
For INTERREG V-A Romania – Bulgaria, project reporting is made through the electronic system eMS. The Programme bodies developed an eMS reporting guide “Reporting in eMS Guidance for lead beneficiaries and partners”. Last updated version is available for download on eMS login page
http://ems-robg.mdrap.ro/app/main?execution=e1s1
There are 2 MAJOR type of reports:
Partner report – made by each partner for his share of activities and expenditures
Project report – made by LB that aggregate information on project level

## Slide 3
PARTNER REPORTS

## Slide 4
PARTNER REPORT
For period “0” all partners must create a partner report. If the respective partner has project preparation expenditures incurred and paid, then these have to be claimed in the partner report 0.1 and submitted for FLC, otherwise directly to LB.
For implementation defined periods, each beneficiary that has expenditure incurred and paid for at least 1.000 Euro, can initiate a partner report in eMS and submit it in the system for FLC verification (a partner report should allways contain the progress of activities).
By exception, partner report 0 and final partner report may be requested for FLC verification even for lower amounts than 1.000 Euro.

## Slide 5: PARTNER REPORT
The reporting section becomes available to project partners as soon as the project has been contracted in e-MS.
Partner reports are used for requesting validation from FLC for expenditure incurred and/or for providing information/progress of activities for project consolidated activities progress report to LB.
Partner reports may cover only activities of individual project partners (without claiming expenditures) in which case they must be submitted in e-MS directly to the LB or they may contain both activities and expenditure of individual project partners which need to be verified by first level controllers (called FLC) in the system - in which case they must be submitted in e-MS to FLC.
If necessary, more than one partner report can be created for a defined period.
The information provided by each partner in their partner reports is then integrated by the LB into project report. Partner reports created by mistake should be deleted (before submitted)!

## Slide 6: PARTNER REPORT
Once the project is contracted, the overview of partner reports will automatically be displayed when a partner is accessing his project Dashboard.
If a user has multiple roles in the system (e.g. lead partner and partner at the same time), it is necessary to select the role from the dropdown menu at the top of the interface called ‘Select role’.
Please note that the lead beneficiaries must create their own partner reports as “PP”, not as “LP”. The LP role is used for creating Project reports.

## Slide 7: Where to submit partner reports

## Slide 8: PARTNER REPORT
By default, it is possible for each partner to create one partner report per period. The creation of other (second, third, etc.) report(s) for a defined period is only possible if the LP contacts the JS officer (via e-MS email for example) and asks for JS permission, by clearly mentioning the partner and reporting period for which such a permission is requested.
When requesting amounts for FLC verification, each partner (including LP) creates their own individual partner reports reflecting their share of activities and expenditure, according to the AF.
In this respect, each partner (including LP) fills in the individual partner report, using their own e-MS account. Each partner report with expenditure is verified by the partner’s FLC in e-MS and then is included by the LP in a project report. Partner reports only with information regarding the progress of activities (with 0 expenditure requested) are submitted by the partners directly to the LP.

## Slide 9: PARTNER REPORT
Each partner should create and submit to the LP at least one such report every 6 months, according to the established schedule for reporting the consolidated progress of activities at project level. If there is no sufficient activity to report on, the partner fills-out all other parts of the report (e.g. problems and deviations, activities if any, forecast for the next report) and submits the partner report with NO expenditure declared directly to the LP.
Attention!
All sections of the partner reports shall be filled in, no section will be left empty.
Information on project activities, output indicators and deliverables must be included, in detail regardless of the fact that the report includes expenditures or not. Reporting on deliverables, incl. upload of evidence of achievement

## Slide 10
PROJECT REPORTS

## Slide 11: CONSOLIDATED PROJECT REPORTS
LB consolidates the project reports and submits them to the Joint Secretariat:
consolidated report for period 0 including all partners’ reports 0.1 (project preparation report),
final consolidated report for last reporting period. The final claim for reimbursement must be submitted together with the final report (within 5 months since the end of the implementation period), irrespective of the amount.
Technical or financial project reports will be separately submitted for all other reporting periods.

## Slide 12: FINANCIAL PROJECT REPORTS
LB has the possibility to ask reimbursement of expenditures to the MA via a financial project report submitted in the electronic system at any given time, for one or more partners, provided that the expenditure claimed for reimbursement is not lower than 5,000 euro ERDF.
These financial project reports will be created by LB only by attaching the available FLC certificates. For financial project reports, no other sections required by the project report template will be filled in.
LB is obliged to create a financial project report in the system requesting amounts for reimbursement from the programme no later than 3 working days from when FLC certificates summing up more than 5.000 Euro ERDF (from all partners) are available in the system, even if not all partners have FLC certificates to be included in the project report.

## Slide 13: TECHNICAL PROJECT REPORTS
LB must create and submit to Joint Secretariat, via eMS project reports including physical progress of the project (art. 6, (10) – subsidy contract):
Every 6 months (submitted within 10 working days since the end of the 6th month);
Reports are based on partners reports submitted in the e-MS. Information shall be aggregated manually by LB;
Does not include FLC certificates / amounts to be requested for reimbursement;
Will include:
  General overview of the progress of the project since its start (section “Highlights of main achievements”);
  Detailed description of the activities performed in the reporting period. Please detail on activities carried out and contribution by the project partners as well as on problems or deviations from the initial plan ;
  Detailed information on the progress achieved in the deliverables (equipment delivered or services provided) during the reporting period
  Detailed description of the project contribution to the output indicators and target groups;
  Detailed information regarding the problems encountered and the solutions found;
  Detailed information on the project contribution to the horizontal principles during the reporting period
  Attention: No section of the project report will be left empty (Not applicable mentioned, if the case), All information must be presented in a clear manner / If not, the report will be reverted

## Slide 14
Exceptions:
a. Preparation costs can be only requested in the first project report (named 0.1 in eMS)! Therefore even if the total amount at project level is below the 5,000 euro ERDF threshold, a project report should be created and submitted to JS.
b. Also, in case the final amounts requested from the programme is below 5.000 Euro, a project report should be created and submitted to JS. If necessary, more than one project report requesting amounts for reimbursement can be created for a defined period. It is mandatory for the LP to create a consolidated project progress report on activities in the system according to the established schedule for reporting the consolidated progress of activities at project level established within the MA Instruction no. 5 for beneficiaries for call 1-hard and call 2 projects and every 6 months for call 3 projects.

## Slide 15: FINAL PROJECT REPORT
is submitted in hard copy (on paper) using the template provided by Annex 19.1 – Final Report (2 original copies;
within 5 months since the end of the implementation period
is signed by the legal representative of the LB;
Is compiling data for the entire project implementation period;
Details on what was realized, where, by whom, what objectives/results/outputs have been achieved/reached, what resources have been used, what problems have been encountered. The reporting presents the information in comparison with the against what was originally planned in the application form;
Attention!
For third call project, if the project contribution to indicators within the final reports is lower compared to the application form, the MA is entitled to decommit project funds by reducing the original project budget and the corresponding ERDF contribution, as follows:
a)10% to the budget of the beneficiaries if project indicators < 75% target (average at project level considering all indicators)
b)25% decommitment to the budget of the beneficiaries if project indicators < 50% target (average at project level, considering all indicators)
c)10% decommitment, in case the project did not contribute to the result indicators (a non-quantifiable one)

## Slide 16
PROJECT PROCUREMENTS

## Slide 17: PROJECT PROCUREMENTS
Online tutorial on how to fill in this section available on Programme website:
https://www.youtube.com/watch?v=vE_Q6AiMI1o&feature=youtu.be
All partners (including LB) shall fill in here the details for their own procurements. In this section each partner will add and visualize only their own procurements with the exception of LB which can visualize all the procurements filled in the system by all partners.

## Slide 18: PROJECT PROCUREMENTS
The following information is mandatory to be fill in procurement section:
Partner responsible for the procurement
Contract type (services/supplies/works)
Contract Number/Contract date; Contract Name
Contract Amount (in Euro)
Eligible expenditure incurred and paid based on contract – when the information is available at partner level
Type of Procurement Procedure Used; Date of launching in National Electronic Procurement System
Contractor Name; Unique Identifier of the Contractor
Please provide short details about the progress of the procurement
If applicable, please describe and justify any problems and deviations including delays from the work plan presented in the Application Form and solution found (e.g. details on re-launching the procedure)

## Slide 19: PROJECT PROCUREMENTS
The entire procurement documentation shall be uploaded in the Upload section of each procurement contract:
procurement files (tender dossier, announcement, bids from tenderers, evaluation reports, award documents, all relevant documents related to this procurement …)
services contract
addenda to the contract
in case of equipment and services procured under a works contract all the related documents will be attached.
Each procurement is available in the List of expenditure of relevant partner and can be linked to an invoice in a partner report. Once such a link is created, and you will request for FLC verification invoices related to a procurement, the list of invoices for each procurement shall be populated. This list can be exported to Excel (by pressing the “Export” button below the list).

## Slide 20: PUBLIC PROCUREMENTS
The Project Procurements section can be filled in at any time during project implementation, so you can fill in procurement details just before you request in the system the first related expenditure.
Recording all the procurements of the project is compulsory!
In case you don’t create procurements in this section, you won’t be able to link the invoice to the procurement when you request it for FLC verification and your FLC request (partner report) shall be reverted!
The documents related to a procurement shall be uploaded only once in this section. The invoices and payment documents will be linked to the respective procurement (via list of expenditure of the partner report. The deliverables shall be uploaded separately in the partner report deliverable attachment section located in the reporting per work packages section and the accounting documents in the partner report attachment section.

## Slide 21
SPENDING FORECAST

## Slide 22: SPENDING FORECAST
In the section Contribution and Forecast of the partner report must fill in forecast spending for the following partner reports of all the periods defined in AF. The system also displays planned budget and actual spending per period.
In the Follow up section the Partner Contribution amount is split automatically by the system!

## Slide 23: SPENDING FORECAST
www.interregrobg.eu