|  |  | MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS |
| --- | --- | --- |

DECISION no. 19

of 16th of January 2017

Regarding the complaints lodged against the Monitoring Committee Decision no. 32 of 8th of December 2016, approving the List of projects proposed for approval, rejection and re-evaluation, submitted in the second call for proposals for the Interreg V-A Romania Bulgaria Programme within Deadline - 15th of March 2016

Having regard to the following:

- Monitoring Committee Decision no. 33 of 8th of December 2016 approving the Complaint Panel for the projects submitted under the second call for proposals, priority axes 4-5 for Interreg V-A Romania-Bulgaria Programme, the Complaint Panel of Interreg V-A Romania-Bulgaria Programme has adopted this:

DECISION

Article 1. The present document rejects the complaint lodged by Foundation Sustainable Development and Prosperity, lead beneficiary of the application code 16.5.2.012 – “Better Administrative Capacity - Better tourism development” and registered by CBC ROC with the number 15865/19.12.2016, appealing some reductions applied to the budget.

Article 2. The reasons for rejection of the complaint

The applicant arguments mentioned within the current appeal are as follows:

Lead Beneficiary:

- The amount of 2,160.00 Euro (Rent of hall - 3 days x 4 TM) was considered not justified and exaggerated in the context of envisaged team meetings;

- The amount of 30,000.00 Euro (S51- Preparation of Guidelines for project implementation) is considered excessive and unjustified, as the expenditure is briefly described in Activity 4 and has not been identified a purpose in the context of the trainings, has no contribution to the indicators and their posting on the website in sustainability is disproportionate with the requested cost;

- The amount of 20,000.00 Euro (S44 - Development of integrated strategy for tourism) was considered unjustified by the description of the service: “External expertise for development of Integrated Study, based on the implemented analysis” as there are envisaged for both RO as well as BG items S43 and S49; the integrated strategy thus is unnecessary and excessive to be contracted; it must be drafted by the relevant beneficiaries involved in the project, supported by the envisaged studies;

- The amount of 1,998.00 Euro (Coffee breaks for the participants - 60 participants + 2 lecturers + 14 project team members + 2 translator = 78 persons x 5 days x 3 trainings x 2 coffee breaks per day – 2340) is exceeding the average value of the 3 submitted offers;

- The package Training materials for the participants - 360 pcs (Notebooks - size A4, spiral spine, 50 pages, paper 60g/m2, Engraved pen - aluminum body, USB flash memory - 64 GB, USB 3.0) was considered overestimated, as the participants, as per section 2.5 - Target groups and description of the activity, are 60; thus 300 packages, in total amount of 8,712.00 Euro, were considered unjustified;

- 4,058.95 euro (Office and administrative costs) and 12,176.86 euro (Staff Costs) - the reduction is due to applying the flat rate to the reductions made to the calculation basis (direct costs).

Beneficiary 4:

- The amount of 1,800.00 Euro* (Meals for the participants - 60 participants + 2 lecturers + 2 translator = 64 persons x 5 days x 3 trainings  - 960) was considered unjustified, in accordance with eligibility rules for external expert envisaged within Annex D - List of eligible expenditures;

- The amount of 297.00 Euro* (Coffee breaks for the participants in BG first workshop - 40 participants + 13 project team members + 2 translator = 55 persons x 3 days x 2 coffee breaks per day) is exceeding the average value of the 3 submitted offers;

- The amount of 600.00 Euro (Organization of opening and closing press conferences for 50 participants in RO - rent of hall, sound equipment, coffee breaks, photos, logistic, secretary - 2 conferences x 50 participants = 100 participants) is representing exceeding amount in relation with Annex C - Ceilings for expenditures.

- € 282.15 (Office and administrative costs) and 846.45 (Staff Costs) - the reduction is due to applying the flat rate to the reductions made to the calculation basis (direct costs).

*The applicants have failed to indicate the cost/item, subject to reduction. It was identified based on the proposed amount for reduction.

The reasons for rejection of the complaint are:

Lead Beneficiary:

- 2,160.00 Euro (Rent of hall - 3 days x 4 TM) - the appeal is rejected  by the Complaint Panel – the applicant does not provide information regarding the location of the envisaged team meetings and no justification why the team meetings should be held in other town than where beneficiaries have offices. Moreover, based on the fact that 3 of the beneficiaries are public institutions and have available rooms, the renting of a hall for team meetings is not justified.

- 30,000.00 Euro (S51- Preparation of Guidelines for project implementation) was proposed for reduction for being excessive and unjustified, as the expenditure is briefly described in Activity 4 and has not been identified a purpose in the context of the trainings, has no contribution to the indicators and their posting on the website in sustainability is disproportionate with the requested cost. The applicants contest the reduction by underlining the important role of the Guidelines in the sustainability period.

Before addressing the argument of the applicants, it should be pointed out that the conclusion of the assessor is fully in line with the information presented in the Application Form. In the first place no description whatsoever of the service, the specific content or the need of such Guideline is provided by the Beneficiaries. On the other hand, although the contents of the Guidelines for project implementation is not described it is only logical that it cannot differ too much from the 2 training modules for project management and implementation proposed to be elaborated (see S50). But even if such Guidelines do have a specific purpose and bring certain added value (which were not explained in the application form and are certainly not implicit) it is only logical that they should be elaborated together with the training modules, i.e. within the same, rather than as a separate service.

And last, but not least consulting 2 of the 3 price offers submitted as evidence of the market price for the elaboration of the Guidelines revealed references to “emergency management” and therefore further confirmed the conclusion that the Guidelines serve no specific purpose within the project. According to the text of the offer, the elaboration of guidelines will follow:

- “Following the most recent EU legislation related to national and EU system for emergency management; planning and emergency response:

- European legal regulations for emergency management; the activities of the fire departments and protection of the population in European cooperation in emergency management”

As regards the argument of the Beneficiary brought up in the current complaint, and namely that the Guidelines will be used in the sustainability period, it should be automatically dismissed for the following reasons:

- It represents new information, which was not mentioned in the Application Form. While in Section 4. Exit/continuation strategy, the applicants mention explicitly the project outputs that will serve as tools for ensuring the project sustainability (Integrated strategy, common commission for integrated tourism and online bulletin), there is no mention whatsoever of the Guidelines for project implementation;

- Ensuring the project sustainability and the related costs are responsibility of the beneficiaries and do not represent eligible, as they do not meet the eligibility requirement of being necessary for initiating and carrying out the project.

- 20,000.00 Euro (S44 - Development of integrated strategy for tourism) was proposed for reduction for being unjustified by the description of the service: “External expertise for development of Integrated Study, based on the implemented analysis” as there are envisaged for both RO as well as BG items S43 and S49; the integrated strategy thus is unnecessary and excessive to be contracted; it must be drafted by the relevant beneficiaries involved in the project, supported by the envisaged studies;

The applicants contest the reduction with the arguments:

- It is very important for the project as it is designed as a response to the problems identified and will strongly improve the common CB process at policy level;

- The strategy is part of the project results stated in section 2.2 and as project output is one of the mechanisms to enhance cooperation capacity;

- To delete the Strategy without a comprehensive research is underestimation of the real problems of the Administrative processes regarding integrated tourism development in both national government authorities;

- The integrated strategy will be based on the findings of the two analysis in Ro and BG and it is completely different documents;

- The relevant beneficiaries involved in the project have different job descriptions as it is written down in the AF. The Tourism Agencies and the responsible authorities implement already developed strategic documents and they don’t develop them.

The decision to cut the related costs is justified for the following reasons:

- In the first place, the subject matter, the need and the purpose of the strategy are unclear. In the dedicated activity (A.3) the applicants provided no description whatsoever of the strategy – they do not even mention its subject matter – it is named simply “Integrated Strategy”. It is however referenced in other sections of the Application Form further calling into question the exact subject and purpose of the Strategy:

Section 1.2 – “Development of Integrated Strategy for improvement of the administrative capacity as a process of government support to the local and regional tourism development business.”

Section 2.1 – “Lack of working tourism policy at the CB-region; underdeveloped national/regional policies for integrated tourism between the authorities and non-government sector – development of Strategy”;

Section 2.5 – “The Strategy will identify and assess the role of PI responsible for tourism development in the eligible region. Since today tourism is turning into a key sector of the economy to generate financial revenues and new jobs, its proper development is of a great importance for the regional well-being. The Strategy will support relevant PI in tourism marketing planning and taking advantages of the CB-region’s natural and cultural resources and potential.”

Section 4 – “The Integrated Strategy will be used by the PI in all eligible regions in order to support their work in local tourism development and application of EU policies, related to tourism.”

Is it a strategy for integrated tourism development designed to address the lack of working tourism policy in the CB region, or is it intended to identify and assess the role of PI responsible for tourism development in the eligible region and propose solutions for the improvement of their administrative capacity? The arguments provided by the applicants on the issue in the present complaint leave this question open, as they invoke both “the common CB process at policy level” and the “real problems of the administrative processes” in the national authorities;

- In the second place, the applicants’ arguments further lead to the confusion of whether the strategy is and output or a result of the project. Either way, it should be noted that the assessors have not “deleted” the strategy, just the costs proposed by the LB. In other words it was not contested the need or the purpose of the strategy, but its contracting by the LB for 2 reasons:

  - The strategy appears to overlap at least partially with the analyses (S43 and S49) proposed to be developed within the same activity. Indeed according to their description within the dedicated activity A.3 the analysis is presented as “a model of mechanism for communication of common problems and solutions. The analysis will study the following stages…Possibilities for development of integrated tourist products, their identification and implementation in the CB area. Development of training methodology and training modules for the target groups to implement the methodology”;

  - Lack of legitimacy on the part of the LB (non-government organization) to elaborate (by subcontracting) a strategy to be used and implemented by government (national) authorities – In both the application Form and the present complaint the applicants indicate the national responsible authorities as the main users of the Strategy. In the first place the BG national authorities/responsible institutions are not even involved in the project and therefore the applicants’ plan that they will implement a Strategy, in the development of which they have had no involvement whatsoever is hardly feasible. The same is true for the Romanian part. In fact provided that Beneficiary 5 - National Institute for Research and Development in Tourism will be responsible for the development of the analyses for the Romanian territory, it is only logical that they should be responsible for the development of the Strategy.

- And last but not least the assessors have requested clarifications on conducting the studies and strategy, but the beneficiaries failed to provide a response.

- 1,998.00 Euro (S62 - Coffee breaks for the participants - 60 participants + 2 lecturers + 14 project team members + 2 translator = 78 persons x 5 days x 3 trainings x 2 coffee breaks per day – 2340) are proposed for reduction due to exceeding the average value of the 3 submitted offers. The applicants contest the reduction, as the price of 3.60 euro is in line with calculation rules provided in the Guidelines and is fully in line with Annex C.

As explained by the applicants they have submitted 3 offers as evidence of the market price for coffee breaks - 2 euro/person (Tra Bil), 3.60 euro/person (Moyri Co Ltd) and 5 euro/person (Eit Corporation). In the first place, it is evident that the proposed 3.60 euro/person is the median value of the three offers, whereas the Applicant’s Guide line provides for not exceeding the average value of the 3 offers. In the second place, as indicated in the price offers attached, the offers are provided for 2 coffee breaks per day per person, which means that the average price per coffee break is 1.77 euro ={(2+3.6+5)/3}/2.

The reduction operated by the assessors for this service was made as follow:

- first reduction was for the coffee breaks for the external experts (2 translators and 2 lectures) = 4 x 5 days x 3 trainings x 2 coffee breaks per day x 3,6 euro = 432 euro (reduction which was not appealed by the Lead Beneficiary).

- The second reduction for the coffee breaks was operated for the rest of the participants due to exceeding the average value of the price offers. The value proposed by the Lead Beneficiary was: (60 target group + 14 staff members = 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 3.6 euro) = 7,992.00 euro

The value proposed by the assessors was: 60 target group + 14 staff members = 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 2.7 euro) = 5,994.00 euro

The difference in amount of 1,998.00 euro is appealed by the Lead Beneficiary.

Thus the eligible cost for the coffee breaks for 60 target group + 14 staff members should be: 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 1.77 euro = 3,929.40 euro. Therefore, the total amount which should be reduced for the respective service is 4,062.60 euro.

- 8,712.00 euro representing 300 sets of Training materials for the participants - 360 pcs (S116 - Notebooks - size A4, spiral spine, 50 pages, paper 60g/m2, Engraved pen - aluminum body, USB flash memory - 64 GB, USB 3.0) are proposed for reduction as the participants, as per section 2.5 - Target groups and description of the activity, are only 60. The applicants contest the reduction with the argument that even if the participants are only 6, they will participate in 3 different trainings.

As evident from the description of the proposed costs training materials package includes a note book, engraved pen and USB flash memory 64 BG, USB 3.0. The total amount for the proposed 360 packages is 10,454.40 euro. Even if the materials are proposed for 6 trainings, provided that those will be attended by the same 60 persons, providing them with a new package (including a 64 USB flash memory for 25.20 euro/piece) for each training is simply unnecessary. As evident even from the present complaint, the applicants failed to explain why one and the same participant would need to receive 6 USB flash memories, 64 GB each, for a total of 151.20 euro.

- 4,058.95 euro (Office and administrative costs) and 12,176.86 euro (Staff Costs) - the reduction is due to applying the flat rate to the reductions made to the calculation basis (direct costs). The applicants request the calculation of the staff and administrative costs upon recovering of the disputed above position.

Taking into consideration that the arguments presented by the applicants against the above detailed direct cost do not lead to the recovery of the operated reductions a new reduction of 2,064.60 euro is proposed, a further reduction of the staff and office and administrative costs should be applied in the amount of 309.69 euro for staff costs and 103.23 euro for office and administrative costs.

Beneficiary 4:

- The amount of 1,800.00 Euro was reduced due to exceeding the average value of the 3 offers. The applicants contest the reduction as the unit price of 3.60 euro is fully relevant to Annex C. There are no offers from Romanian companies attached to the project proposal for provision of this service and therefore the applicants consider that the conclusion of the assessors is a technical mistake.

In the first place, it should be note that the applicant failed to indicate which the service, subject to reduction is. And while based on the arguments presented, and more precisely the indicated unit price the applicant appears to contest the reduction operated for coffee breaks, the indicated value of the reduction (based on the notification of the assessment result - point 1 for Beneficiary 4) refers to meals for participants in the training (Meals for the participants - 60 participants + 2 lecturers + 2 translator = 64 persons x 5 days x 3 trainings - 960). Therefore we shall examine both reductions:

- 1,800.00 euro (Meals for the participants - 60 participants + 2 lecturers + 2 translator = 64 persons x 5 days x 3 trainings – 960) are reduced as those are not in line with eligibility rules for external expert envisaged within Annex D - List of eligible expenditures.

The reduction of 1,800 euro refers to the meals envisaged for the 2 lecturers and 2 translators. And indeed while Annex D explicitly provides for the eligibility of the costs for travel and accommodation for external experts and service providers (under External expertise and services), it does not provide for the eligibility of the cost for meals. The price for the respective service should include the administrative and other costs to be incurred by the service provider/ external expert related to rendering the service. And while the costs for travel and accommodation are dependent on the location of rendering this service and cannot be included in the price in advance, the costs for meals are not and therefore are normally included in the price for the service;

- 1,998.00 Euro (Coffee breaks for the participants - 60 participants + 2 lecturers + 14 project team members + 2 translator = 78 persons x 5 days x 3 trainings x 2 coffee breaks per day – 2340) is reduced for exceeding the average value of the 3 submitted offers;

Indeed as claimed by the applicants, the proposed costs are not supported by offers from Romanian companies. However, contrary to the claim of the applicant, it is not included in Annex C either. Therefore, provided that the proposed price is the same as the price proposed by the LP (which is supported by 3 offers) and the AG does not have any requirements in terms of origin of the offers, the assessors have accepted the 3 offers submitted by the LB (2 euro/person -Tra Bil), 3.60 euro/person -Moyri Co Ltd and 5 euro/person - Eit Corporation p.) as evidence of the market price for the same service envisaged by B4.

But taking into consideration that the price offers are provided for 2 coffee breaks per day per person, the average price per coffee break is calculated at 1.77 euro = {(2+3.6+5)/3}/2.

The value proposed by the Lead Beneficiary was: (60 target group + 14 staff members = 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 3.6 euro) = 7,992.00 euro

The value proposed by the assessors was : 60 target group + 14 staff members = 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 2.7 euro) = 5,994.00 euro

Thus the eligible cost for the coffee breaks for 60 target group + 14 staff members should be : 74 persons x 5 days x 3 trainings x 2 coffee breaks per day x 1.77 euro = 3,929.40 euro. Therefore, the total amount which should be reduced for the respective service is 4,062.60 euro

- 297.00 Euro is reduced for exceeding the average value of the 3 submitted offers. In the first place, it should be note that the applicant failed to indicate which the service, subject to reduction is. Based on the value of the proposed reduction and the indicated unit price, we assume that the applicants actually contest the reduction proposed for Coffee breaks for the participants in BG first workshop  (40 participants + 13 project team members + 2 translator = 55 persons x 3 days x 2 coffee breaks per day). The applicants contest the reduction as the unit price of 3.60 euro is fully relevant to Annex C. There are no offers from Romanian companies attached to the project proposal for provision of this service and therefore the applicants consider that the conclusion of the assessors is a technical mistake.

Indeed as claimed by the applicants, the proposed costs are not supported by offers from Romanian companies. However, contrary to the claim of the applicant, it is not included in Annex C either. Therefore, provided that the proposed price is the same as the price proposed by the LP (which is supported by 3 offers) and the AG does not have any requirements in terms of origin of the offers, the assessors have accepted the 3 offers submitted by the LB (2 euro/person - Tra Bil), 3.60 euro/person -Moyri Co Ltd and 5 euro/person - Eit Corporation p.) as evidence of the market price for the same service envisaged by B4.

But taking into consideration that the respective price offers are provided for 2 coffee breaks per day per person, the average price per coffee break is calculated at 1.77 euro = {(2+3.6+5)/3}/2.

The value proposed by the assessors was: (55 participants x 3 days x 2 coffee breaks per day x 2.70 = 891 euro, which means a reduction of 297.00 euro (1,188.00 – 891 = 297.00);

Thus the eligible cost for the coffee breaks for 55 participants should be:  55 participants x 3 days x 2 coffee breaks per day x 1.77 = 584.10 euro.  Therefore, the total amount which should be reduced for the respective service is 603.90 euro

- 600.00 Euro (Organization of opening and closing press conferences for 50 participants in RO - rent of hall, sound equipment, coffee breaks, photos, logistic, secretary - 2 conferences x 50 participants = 100 participants) are reduced for exceeding the applicable ceiling from Annex C- Ceilings for expenditures. The applicants contest the reduction as the unit price is fully relevant to Annex C.

The unit price proposed by the applicant is 36.00 euro with VAT or 30.00 euro without VAT. The proposed price and services included are applicable to organisation of project events. The ceiling provided for press conferences is 25.00 euro without VAT, or 30.00 euro with VAT. Using the correct ceiling, the eligible costs amount to 100 participants x 30.00 euro = 3,000.00 euro, resulting a reduction of 600.00 euro (3,600 – 3,000 = 600)

- 282.15 euro (Office and administrative costs) and 846.45 euro (Staff Costs) - the reduction is due to applying the flat rate to the reductions made to the calculation basis (direct costs). The applicants request the calculation of the staff and administrative costs upon recovering of the disputed above position.

Taking into consideration that the arguments presented by the applicants against the above detailed direct costs do not lead to the recovery of the operated reductions and a further reduction of 2,371.50 euro is proposed, a further reduction of the staff and office and administrative costs should be applied in the amount of 355.73 euro for staff costs and 118.58 euro for office and administrative costs.

Article 3. The decision of the Complaint Panel is final, binding to all parties and not subject of any further complaint proceedings within the Programme.

| Member 1 of Complaint Panel – Managing Authority representative, Ministry of Regional Development, Public Administration and European Funds, Romania | Member 2 of Complaint Panel – National Authority representative, Ministry of Regional Development and Public Works, Bulgaria | Member 3 of Complaint Panel –External expert, Ministry of Regional Development, Public Administration and European Funds, Romania |
| --- | --- | --- |
| Signature | Signature | Signature |