|  |  | MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS |
| --- | --- | --- |

DECISION no. 14

of   16th of January 2017

Regarding the complaints lodged against the Monitoring Committee Decision no. 32 of 8th of December 2016, approving the List of projects proposed for approval, rejection and re-evaluation, submitted in the second call for proposals for the Interreg V-A Romania-Bulgaria Programme within deadline – 15th of March 2016

Having regard to the following:

- Monitoring Committee Decision no. 33 of 8th of December 2016 approving the Complaint Panel for the projects  submitted under the second call for proposals, priority axes 4-5 for Interreg V-A Romania-Bulgaria Programme,

- the Complaint Panel of Interreg V-A Romania-Bulgaria Programme has adopted this:

DECISION

Article 1. The present document rejects the complaint lodged by Balchik Municipality, lead beneficiary of the application code 16.5.2.011	 “Network for smart cooperation of Black Sea communities in the cross- border region” and registered by CBC ROC with the number 15862/19.12.2016, in which formulates objections against the MC decision for budgetary reductions for services S30 and S32.

Article 2. The reasons for rejecting the complained budgetary reductions are:

| 17,680 Euro – S30 Elaborating strategy service | Complaint rejected The service is not justified due to the fact that the complainant did not provide proper justification for elaboration of two separate strategies for each of the two countries and it is not tackled the issue of better understanding the specific problems. As well, in the description of Activity 7 from the application form there is made reference to a strategy for the “territory of the Black Sea municipalities in the cross- border area”, to “joint strategy”, “the policy”, “the document”, a strategy that has joint character, aiming cohesion and cooperation of both communities. Moreover, there are envisaged 2 services for the same price, which is unjustified by the activity description and supporting offers. The decision of cutting the costs of one strategy is justified also by the fact that there is envisaged a similar service S29 Elaborating strategy service for Lead Beneficiary. |
| --- | --- |
| 69,118.63 Euro – S 32 Creating integrated information system | Complaint rejected For the creation of integrated information system service within Activity 8, the assessors reduced the level of the proposed expenditure to the same level as that for the LB service S31- Creating integrated information system service within Activity 8, based on the principle of sound financial management. The complainant is stating in his request that, although there are the same types of services, there are differences between the softs (without providing the differences) and the amount of information is different as per the size of the population of the 2 municipalities. The complaint cannot be taken into consideration based on the fact that the complainant has not indicated in the complaint the differences to justify why a similar soft is 3 times more expensive, the difference concerning the size of the populations of Balchik and Navodari is not so big and both services provide the same functionality. |

Article 3. The decision of the Complaint Panel is final, binding to all parties and not subject of any further complaint proceedings within the Programme.

Signed by

Members of the Complaint Panel

Signature

Member 1 – Managing Authority representative, Ministry of Regional Development, Public Administration and European Funds, Romania

Signature

Member 2 – National Authority representative, Ministry of Regional Development and Public Works, Bulgaria

Signature

Member 3 –External expert Ministry of Regional Development, Public Administration and European Funds, Romania