|  |  | MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS |
| --- | --- | --- |

DECISION no.

of ….. of December 2016

Regarding the complaints lodged against the Monitoring Committee Decision no. 30 of 14th of November 2016, approving the List of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – September Deadline – hard projects

Having regard to the following:

- Monitoring Committee Decision no. 31 of 14th of November 2016 approving the Complaint Panel for hard projects – first call – Interreg V-A Romania-Bulgaria Programme,

- The Complaint Procedure of Interreg V-A Romania-Bulgaria,

the Complaint Panel of Interreg V-A Romania-Bulgaria Programme has adopted this:

DECISION

Article 1. The present document partially approves the complaint lodged by territorial administrative unit HARSOVA TOWN, lead beneficiary of the application code 15.2.1.098 – “A CROSS BORDER UNION IN THE SHADOW OF HISTORY”.

Article 2.1. The reasons for approving/rejecting the complained budgetary reductions are:

| Complained budgetary reductions for the Lead beneficiary (LB) |  |
| --- | --- |
| 266.10 Euro provisioned under budget chapter Project Preparation | Complaint rejected. The amount of 266.10 Euro has no correspondence in the description of the activity Project preparation (pg. 18 of the application form). According to the Applicant Guide, preparation costs should be incurred before the submission of the application. The application budget foresees 52.778.92 Euro for project preparation for the LB, while the activities described in section 2.3 of the application form gather only 52.512,82 Euro (services for archeologist – 766.95 Euro and taxes – 141.12 Euro, preliminary design: architects and designers - 39370.08 Euro and archeologist – 4090.90 euro, licensed consultant for development of assessment of the compliance of the preliminary design with existing requirements for construction works – 5828.82 Euro, state tax for coordination of the preliminary design – 781.05 euro and translation of documents – 1533.90 Euro). |
| 18,000.00 Euro, envisaged under Activity 7, E1- Delivery of off road car | Complaint rejected. The purchase is not considered duly justified having in mind the description of activity 7 from the application form (the LB regularly inspect the construction site, while it will also be contracted site supervision - 49084.77 Euro, author supervisor - 36813.58 Euro and investment and quality control expert – 25542.39 Euro), corroborated with the amounts foreseen for Activity 1 – Overall project management (10800 Euro for each beneficiary for transport, accommodation and daily allowance). The ground for this budgetary reduction is not the lack of eligibility according to Applicant’s Guide, Annex D – Eligibility of expenditure, but the lack of duly justification of the necessity of the costs for achieving the project objectives and results. |
| 140924,29 Euro for infrastructure and works, of which: |  |
| 80,215.47 Euro (General construction works – 38,146.90 euro, Installation works – 8,535.10 euro, Furniture and equipment - 33,533.47 euro) representing construction, furnishing and equipment related to the designed on the second floor - 9 rooms for archeologist with individual bathrooms, a cafeteria, and a kitchen | Complaint rejected. It is not proven the necessity of the costs related to the 9 rooms with individual bathrooms, cafeteria and kitchen for achieving the project objectives and results. The ground for this budgetary reduction is not the lack of eligibility according to Applicant’s Guide, Annex D – Eligibility of expenditure, but the lack of duly justification of the necessity of the costs for this application. The respective part of the investment was included in the preliminary design, but no information was initially provided within the description of activities, as well as within the Annex 7 – Cost benefit analysis (no operating/maintenance costs are considered; the possibility of generating revenues is not taken into account). The clarifications provided by the applicant are not considered sufficient to justify the necessity of the respective costs. Regarding the LB argument that it can be a problem for the building permit to be obtained in case the second floor of the building is not also renovated, please note that this argument can’t be accepted as justifying the necessity of considering the respective costs eligible in the overall context of this application, but should be treated as a project implementation risk in case the application is contracted. |
| 1,023.47 Euro, provisioned under budget chapter Infrastructure and works | Complaint rejected. The amount was reduced for missing correspondence with the activities. For this specific amount, no clear contra arguments were provided by the Lead Beneficiary who contested the entire amount proposed for reduction from the budget category Infrastructure and works. |
| 59,685.35 Euro, representing the total amount of net revenues estimated to be generated by LB investment | Complaint rejected. According to the Applicant Guide (section I.8) and Application Form template (section 3.1) the application budget shall not include the net revenue (the generated net revenues as indicated by the cost-benefit analysis are deducted from the investment cost, thus establishing the eligible costs of the project). Considering the information filled-in in section 2.8. Revenue generation of the Application Form, as well as the Annex 7. Cost – benefit analysis provided for investment of the Lead Beneficiary, the reduction of the net revenues estimated to be generated by LB investment is considered justified. For this specific amount, no clear contra arguments were provided by the LB who contested the entire amount proposed for reduction from the budget category Infrastructure and works. |
| Complained budgetary reductions for beneficiary 3 |  |
| 3,000 euro, representing related costs with procurements for E1 and E2 | Complaint rejected. Expenditure is related to the purchase of two cars that were reduced from the budget. |
| 9,000 euro, Activity 11- Development and realization of expositional plan in the TIC of ARUO and promotion of the joint tourist product for “assistance of archaeologist” | Complaint approved. According the national legislation the beneficiary is obliged to hire an expert – archeologist in this case (Cultural heritage Act, Ordinance 4/10.08.2013 Art.8, Para.1 p.5 , Ordinance 6/29.06.2007, Art.3, para.1, p.4/в) |
| 62,086.48 euro foreseen under Activity 11, S16 - Services for design of a museum exposition in the TIC | Complaint approved. The information provided by the applicant is observing the conditions of the Applicant Guide for this call for proposals. The amount will be reintegrated in the budget. |
| 10,800.00 euro for item Film for the process of restoration of the two sites exceeding ceilings from Annex C to the Applicant Guide (55 min / 20000€) | Complaint rejected. According to the provisions of the Applicant Guide, “In case the service which is going to be purchased is not following the list of ceilings, the proposal to exceed the ceiling will be analyzed, provided a proper and clear justification is provided, as well as the related supporting documents (including 3 offers or an independent evaluation of the cost). The proposal will be analyzed and will be subject to acceptance / rejection from the evaluators.” In the current case no such justification was provided by the applicant within the Application Form or clarifications. Only in the complaint it is stated that the technical specifications of the proposed films exceed the specifications from Annex C – Ceilings list, but the justification on the necessity of having superior technical specifications for the film is missing. Also only in the complaint the applicants mention that the proposed “film for the process of restoration of the two sites” was considered different than the “information film” the ceiling list refers to. |
| 2,249.10 euro, for Activity 5, S8, and Activity 6, S9, namely Ensuring the expertise of an independent archeologist | Complaint approved. The amount will be reintegrated in the budget. |
| 18,000.00 euro, envisaged under Activity 7, E2- Delivery of off road car | Complaint rejected. The purchase is not considered duly justified having in mind the description of activity 7 from the application form (implemented by the LB), corroborated with the amounts foreseen for Activity 1 – Overall project management (10800 Euro for each beneficiary for transport, accommodation and daily allowance). The ground for this budgetary reduction is not the lack of eligibility according to Applicant’s Guide, Annex D – Eligibility of expenditure, but the lack of duly justification of the necessity of the costs for achieving the project objectives and results. |

Article 2.2. The corresponding (flat-rate based) amounts for Staff costs and office and administrative costs shall be revised accordingly.

Article 2.3. The new budget shall be submitted to the Monitoring Committee for approval and the lead beneficiary shall be informed accordingly on the content of the MC decision.

Article 3. The decision of the Complaint Panel is final, binding to all parties and not subject of any further complaint proceedings within the Programme.

| Member 1 of Complaint Panel – Managing Authority representative, Ministry of Regional Development and Public Administration, Romania | Member 2 of Complaint Panel – National Authority representative, Ministry of Regional Administration and Public Works, Bulgaria | Member 3 of Complaint Panel – National Authorities Department representative, Ministry of Regional Development and Public Administration, Romania |
| --- | --- | --- |
| Signature | Signature | Signature |