|  |  | MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS |
| --- | --- | --- |

DECISION no.

of ….. of December 2016

Regarding the complaints lodged against the Monitoring Committee Decision no. 30 of 14th of November 2016, approving the List of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – September Deadline – hard projects

Having regard to the following:

- Monitoring Committee Decision no. 31 of 14th of November 2016 approving the Complaint Panel for hard projects – first call – Interreg V-A Romania-Bulgaria Programme,

- The Complaint Procedure of Interreg V-A Romania-Bulgaria,

the Complaint Panel of Interreg V-A Romania-Bulgaria Programme has adopted this:

DECISION

# Article 1. The present document rejects the complaint lodged by Association for Inter-Community Development of Public Utilities for the Water Supply and Sewage Service “Oltul”, lead beneficiary of the application code 15.3.1.053 – “Improvement of the institutional capacity of intervention in case of emergency  situations in border area Olt - Gorna Oryahovitsa (IICES)” and registered by CBC ROC with the number 14479/25.11.2016, appealing the score received on quality/technical assessment criteria Q18 and Q26 and thus the project rejection according to the MC Decision no. 30/14.11.2016.

Article 2. The reasons for rejection of the complaint are:

- The applicant appeals the score received for Q18 - “Is there a logical link (correlation) between problems, objectives, resources, activities, outputs and results?” (0 points out of 5 points) – rejected by the Complaint Panel.

The main arguments stated in the appeal are as follows:

- the present project is a continuation of an already implemented project financed by Ro-BG CBC 2007-2013 – project MIS-ETC 359, within which was set up a water monitoring system, and therefore the proposed solution for extending the existing system and its administration represent is very cost-effective effort as it does not require the procurement of new hardware and software components; In this sense the assessors conclusion regarding the lack of clarity on the location of the specific equipment, and the administration, management and maintenance of the system, which led to the proposal for project rejection based on criteria Q18 and Q26 are incorrect and they have disregarded the actual information provided in the application form and reiterated in the subsequent clarifications;

- Provided that the elements assessed and scored at criteria E17, Q6, Q7, Q14, Q15, Q16 are interrelated with the elements to be assessed at criteria Q26, and those were assessed as adequate, the score granted for Q26 is inconsistent;

- The score obtained after the evaluation has not been communicated to the beneficiaries.

The appeal submitted by the Lead Beneficiary could not be taken into consideration and accepted in view of the following aspects:

- The arguments of the assessors in terms of lack of information/clarity on the location where the special equipment is to be mounted, administration, operation and management of the water monitoring system proposed by the LB are all based on the findings within the reports of the external technical experts. Provided that those findings represent the opinion of persons with specific technical competences in the field, they are not subject to verification/confirmation in the present complaint verification process. In this sense the issue in concern is whether those deficiencies have been correctly interpreted as lack of correlation between problems, objectives, resources, activities, outputs and results.

- Considering the clarification provided it can properly called in question the needs identified by the LB, i.e. the necessity of the proposed specific equipment as long as the specific locations (i.e. potential industrial pollutants discharging waste waters) have not been identified. As far as the potential pollutants not yet identified, how do we know that they even exist in the proposed localities and, assuming that they exist, how many are they or whether they actually influence the rates of the parameters which are proposed to be monitored, and no other types of parameters. The Applicant’s response to this question “The necessity from purchasing of the items in the proposed quantities described in the project is not influenced by the locations where all the equipment envisaged to be purchased by both Beneficiaries (LB and B2) will be installed/mounted” without any further explanation or argument provided in the clarifications or in the  present complaint confirms that the proposed solution, i.e. the upgrade of the water monitoring system set up in the project MIS-ETC 359 is not based on actual problems and needs related to water pollution risks. Considering that the applicant has not identified the actual problems and needs to be addressed in the project, any further claims for correlation between objectives, results outputs activities and resources are groundless.

- The project activities are not clearly enough described:

- In point 2.1, section 2 Project description of the AF there are stated the problems which represent the common territorial challenges that will be tackled by the project: “therefore, the proposed project addresses the common challenges in Romania-Bulgaria cross-border area in terms of climate change and natural disasters by improving the institutional capacity of intervention in case of emergency situation and implementing an integrated system for risk management on both sides of the border”. Although the fact that the problems are defined and supported by statistical data, it is not clearly described how the “integrated system for control and monitoring” and the “implementing the water monitoring system” will work and what is its added value;

- The description of the “Integrated system for control and monitoring”, subject to the project and defined in Activity 4 is given in a very general way: “the implementation will be carried out according to the signed service and/or supply contract as a result of relevant public procurement procedures for Bulgarian beneficiaries. Each beneficiary will be responsible for its budget and for each signed contract as a result of the relevant procedure of procurement organized” (ref. point 2.3 Project activities of the AF).

- The locations of the “integrated system for control and monitoring” were not indicated and linked with the information provided within the AF, so also ensuring of the sustainability of the project results is not clear enough;

- How the population from Romania and Bulgaria will be warned;

- How and where the “integrated system for control and monitoring” and “implementing the water monitoring system” will be set up based on the risk assessment, considering the different regions (for example each region could have specific risks, depending on its location), type of risks (natural, technological, other risks), each region could have different need of such systems and based on the interrelation with already set up such systems;

- The establishment, functions and administration of the “crisis management center” are not described.

- How the “integrated system for control and monitoring” and “the water monitoring system” will be administrated / managed during and after the project implementation period;

The lack of clarity on the administration, operation and management of the water monitoring system proposed by the LB, which is invoked based on the findings of both external experts, is clear indication of the incoherence between project objectives and outputs and resources. The Technical Memorandum, submitted by the LB as part of Annex A.9 Feasibility Studies/ equivalent technical documents (pp. 367 m- 402 of the AF) makes series of references to the Olt Water Company and its attributions:

“The system allows the management of the contracts signed with the consumers” – p. 298

“All data from the discharge into drain points will be collected and transmitted to a dispatch of the Regional Company” – p. 298

“A measure that can be adopted by the Regional Operator Company is to impose the “polluter pays principle” – p. 288

“the implemented system is able to manage contracts with economic agents and automatically  calculated pollution penalties”

which not only confirm the conclusions drawn by the external technical experts with regard to the lack of clarity in terms of who and how will the system be administered, managed and operated, but clearly call into question the achievement of the proposed project objective (defined within the AF as “Increasing the joint risk management in the Romania-Bulgaria border area by strengthening the institutional and technical management capacity in case of water and air pollution, fire disaster and response in emergency situations”) through the proposed extension of the waste and drinking water monitoring system.

Furthermore, one cannot but observe that while the common problem to be addressed by the project, as defined and detailed within section 2.1 of the AF (“the proposed project addresses the common challenges in Romania-Bulgaria cross-border area in terms of climate change and natural disasters”) strictly refers to climate change and natural disasters, the proposed by the LB extension of the monitoring system for industrial waste water and drinking water tackles the man-made environmental risks of water pollution by industrial operators.

Another issue that cannot be left unnoticed is the relevance of the proposed drinking water monitoring component of the investment in the context of the proposed project objectives, as well as specific objective of the priority axis 3. The final purpose of this component seems to serve the functionality of the water supply services delegated by the LB to Olt Water Company.

- The clarifications provided related to the specific character of the equipment envisaged to be purchased by the Lead Beneficiary and the exact locations where the equipment will be fixed were not proposed within the initial Application form, being considered new information and representing improvement of the content of the initially submitted Application form.

- Related to the activity explaining the process for selection of the exact locations, the beneficiaries emphasized that the selection process will be realized in the first part of the project implementation stage, but at the same time as it could be observed from the Application Form, activity 5, technical assistance (which is the only activity envisaged related to the technical implementation and assistance for activity 6) with main result “technical documents in implementation period” is envisaged to be implemented starting from the “9th month of the project implementation period until month 20th”, period which is overlapping the period envisaged for implementation of activity 6 implementation of water monitoring system. In view of all the above miscorrelations, terms of references for the envisaged service S8 technical consultancy services as regards of the implementation of activity 5 were requested with the special remark that from the information provided within the Application Form, the concept of the Activity 5 is related to completion of the technical part (including adding new sensors; their installing’ analyses and integration of new components), respectively no information about the selection process and analysis of the locations was provided. After clarifications, the beneficiaries provided the terms of references for technical consultancy service (S8) envisaged, respectively it is including also the “technical assistance and support on determining a location for sensors that will be installed in the ground”, aspect which is not envisaged in any section of the Application Form, being also considered as new information which represents improvement of the initially submitted Application Form.

- Also, it should be emphasized that the amount envisaged for purchasing of the special equipment for the Lead Beneficiary represents approximatively 45.53% from the total project budget was not duly justified by presenting of clear and feasible concept about the system envisaged to be established, concept including all the necessary components, so it could be concluded that logical link between the very significant percentage from the envisaged project budget and the proposed project activities/strategy for ensuring of the sustainability for the equipment which will be purchased was not attested and duly justified.

The external expert who made analysis of the project proposal from technical and qualitative point of view of Romanian component, concluded that “the project is not achievable, in respect with Romanian legislation and Applicant’s Guide provisions. The project proposal is not duly consistent from legal/administrative and technical points of view. There are missing important information for a comprehensive evaluation process and some administrative procedures were bypassed”.

Considering the above mentioned, the score granted for this criterion remains of zero points.

- The applicant appeals the score received for Q26 - “Do the beneficiaries have a clear and feasible plan for the sustainability of project results and the capacity to implement it? (0 points out of 2 points) – rejected by the Complaint Panel.

  - the applicant’s argument is that “considering the fact that criteria E17, Q6, Q7, Q14, Q15, Q16, that have in componence elements of criteria Q26, were considered adequate, the statement that the criteria Q26 was not fulfilled, we consider it wrong.”   .

With reference to the abovementioned, the related justification of the score granted by the assessors was reviewed and it should be pointed out that, even if for some criteria significant scores were granted (to be noted that for criterion Q7 there was granted an average score of 4 points and not 8 points, as applicant wrote in the complaint letter), the comments provided calls into question the viability of the proposal. For instance, regarding Q6 the Romanian technical expert concluded: “As proposed, the project will not be able to create operational outputs on the end of implementation process. Will be achieved a list of expensive equipment without clear answers to the following questions…”; for criterion Q7 “(…) The results of the project could be considered realistic. The main issue is that for now is impossible to consider this proposal as an acceptable one.(…)”. Considering the technical experts’ reports even if realistic under certain conditions, the project proposal is not feasible and the purpose of the proposed investment is questionable.

Moreover, in the context of the complaint, besides the complainant’s argumentation, considering that “a clear and feasible plan, for installing, maintenance and management of the equipment is specified neither for the project implementation period, nor after its end for which clarifications were requested”, as well as the conclusions of both technical experts (RO expert- no clear feasible plan, serious inconsistencies within Annex 7- Cost benefit analysis; BG expert - partially with serious weaknesses), the score granted for this criterion remains of zero points out of maximum 2 points.

The last point within the complaint is that the score obtained after the evaluation has not been communicated to the beneficiaries. With reference to this issue, the proposal was granted with 0 points for criteria Q18 and Q26, for which it is stated within Annex B- Evaluation grids to Applicant’s Guide that “Project is proposed for rejection”. Considering the Assessor’s Guide provisions (page 18) “For each of the assessment stages (administrative compliance, eligibility, quality/technical assessment), if there is a clear reason for project rejection (for example: a mandatory criterion is clearly not fulfilled, without the need for clarification on the matter) no clarification letter will be sent and the assessment process will stop automatically at the respective assessment stage”, the assessors decision, not to continue the assessment with criteria “Value for money” is justified, as would have been pointless in view of the fact that project would have been rejected anyway regardless of the granted score for Q27 and Q28, as well as for the other criteria within quality assessment. In this regard the project was not granted a total average score and therefore there was no score to be communicated.

Article 3. The decision of the Complaint Panel is final, binding to all parties and not subject of any further complaint proceedings within the Programme.

Signed by

Members of the Complaint Panel

Signature

Member 1 – Managing Authority representative, Ministry of Regional Development and Public Administration, Romania

Signature

Member 2 – National Authority representative, Ministry of Regional Administration and Public Works, Bulgaria

Signature

Member 3 – National Authorities Department representative, Ministry of Regional Development and Public Administration, Romania