|  |  | MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS |
| --- | --- | --- |

DECISION no. 27

of 15 of December 2015

Regarding the complaints lodged against the Monitoring Committee Decision no. 16 of 15th of October 2015, approving the list of approved and rejected projects submitted in the first call for proposals for the Interreg V-A Romania-Bulgaria Programme – June Deadline – soft projects

Having regard to the following:

- Monitoring Committee Decision no. 17 of 15th of October 2015 approving the Complaint Panel for soft projects – first call – Interreg V-A Romania-Bulgaria Programme,

- The Complaint Procedure of Interreg V-A Romania-Bulgaria,

the Complaint Panel of Interreg V-A Romania-Bulgaria Programme has adopted this:

DECISION

Article 1.1. The present document approves with amendments the second complaint lodged by Civil Association for Development, lead beneficiary of the application code 15.2.1.003 – “The Path of the Clay” and registered by CBC ROC with the number 13127/17.11.2015, appealing the rejection of the first complaint no 11449(1)/23.10.2015.

Article 1.2. The applicant claims that no clarifications were requested during the evaluation process for explicatory information of the data included in the application form. The Assessment Working Group has formulated and submitted to the applicant, using the contact details indicated in the application form, the clarification request no. 131/08.07.2015 (ROC no. 7351/08.07.2015). No answer was received from the applicant. We have attached to this decision the proof of submitting the clarification request no. 131/08.07.2015 (ROC no. 7351/08.07.2015).

Article 1.3. The Complaint Panel shall analyze the information brought forward by the Lead Beneficiary in the complaint based on the data provided on the application form and clarifications. No other information that may alter the quality or content of the assessed application shall be taken into consideration by the Complaint Panel.

Article 2.1. The justifications for approving with amendments the complaint are the following:

Lead Beneficiary:

- Point 3 - The applicant appeals the proposed reduction of the amount of 10,800.00 euro for speakers' fees within activity 7 - Training in sculptural technique as it was not justified in terms of price – rejected by the Complaint Panel.

As no offers or independent evaluation of the costs were provided by the applicant within the application form, the reduction of 10.800,00 euro for speakers' fees made within the evaluation process is justified. The argument of the applicant that the proposed amount observes the provisions of Annex C related to “Coaching services” (row 605) - and thus 3 offers or 1 independent opinion were not needed - is not valid since the coaching services - as services for professional/career consulting, orientation and counseling - cannot be assimilated to speakers/lecturers with an expertise suitable for a training in sculptural technique.

- Point 4 – The applicant appeals the proposed reduction of 3,276.00 EUR, representing the costs for accommodation and food for 6 persons, taking part in the Training in sculptural technique within activity 7 – partially accepted as follows:

Based on the activity description 50 young people from Romanian and Bulgaria will be trained in sculptural technique, the assessors have requested clarifications regarding the number of 56 persons, for which costs for accommodation and food were envisaged Request of Clarifications). Since no response whatsoever was provided by the applicant, the respective costs were reduced accordingly.

Based on the arguments provided in the complaint and on the information included in the application form “the students will assist the lecturers as volunteers. Costs for accommodation and food of 56 people x 7 days х 78€=30 576.00 € VAT included” it can be considered as that 3 of these 56 people are the volunteer students. The applicant argument that the other 3 persons (the difference to 56 – 50 youths and 3 volunteer students) are the members of the project team implementation is no valid since no such information were included in the application from – activity 7. Even so, the costs related to accommodation and food for the project team implementation should not be included under the budgetary line “External expertise and services”, but under the budget category “Travel and Accommodation costs”.

Thus, the costs related to accommodation and food for the 3 volunteer students are accepted: 3 persons X 7 days X 78 Euro = 1,638 Euro.

The reduction of 1,638 euro, related to the costs with the accommodation and food for the other 3 persons (regardless they are the members of the project implementation team) made within the evaluation process should be maintained.

- Point 5 - The applicant appeals the proposed reduction of 142 euro representing costs for 20 plates for pottery artefacts envisaged within activity 7 “Training in sculptural technique”  – accepted

According to the application form “the LB will implement a tender procedure for selection of an external contractor for the delivery of all needed materials for clay modeling which will be used in the training, workshops and festivals”, thus, the argument is accepted.

The costs related to the 20 pottery artefacts are accepted: 142 euro.

- Point 6 - The applicant appeals the proposed reduction of the amount of 936 euro, representing the costs for food and accommodation for 3 persons in addition to the 50 participants, estimated to take part in the 2 workshops within activity 8 - accepted

Based on the information included in the application form “The LB – students volunteers will lead the workshops in both Romania and Bulgaria”, it can be considered the 3 persons as being 3 volunteer students, and thus the costs related with their accommodation and food are accepted.

The costs related to accommodation and food for the 3 volunteer students are accepted: 3 persons X 2 days X 78 Euro x 2 workshops = 936 Euro.

- Point 7 - The applicant appeals the proposed reduction of the amount of 5.000,00 euro for curator services within activity 11 - New open air museum of clay art -  rejected by the Complaint Panel.

The applicant argues that the proposed amount of 5.000.00 euro is within the ceiling envisaged within Annex C for “Expert services” (row 446). The ceiling invoked, as detailed in Annex C, refers to expert services in civil constructions and road infrastructure and cannot be assimilated to the curator services. Therefore, 3 offers or an independent opinion should have been submitted by the applicant for supporting the related costs. A clarification request on this issue has been submitted during the evaluation process to the applicant, but the applicant provided no answer.

Thus, the reduction of 5,000 euro for curator services, made within the evaluation process should be maintained.

- Point 8 - The applicants appeal the proposed reduction of the amount of 835.62 euro, representing the difference between the proposed by the applicants within activity 7 amount of 1,548.12 euro for 70 tool sets of instruments for clay modeling (70 sets x 21.12 euro/each = 1,548.12 euro). Also, the applicant states that the average amount in the link including the 3 offers is not 14.25 euro/unit as evaluators set during the evaluation process - partially accepted as follows:

According to the application form “the LB will implement a tender procedure for selection of an external contractor for the delivery of all needed materials for clay modeling which will be used in the training, workshops and festivals”, thus, 70 tools sets are accepted, at the unit cost set by the evaluators of 14.25 euro.

Thus, the costs related to the 20 tool sets are accepted: 20 tool sets x 14.25 euro/unit = 285 euro.

As regards the unit cost set by the evaluators, the argument provided by the applicant is not clear. The cost unit proposed by the applicants value of 21.12 euro actually represents the value of the highest offer provided (43.24 BGN). The other 2, much lower offers, however, are for different than the proposed by the applicants tool set with 18 pieces – one is for 3 - piece tool set and the other one probably for 8 (the number of pieces is not specified, but it is visibly not 18).

- Point 9 – The applicant appeal the proposed reduction for dry pastels. - partially accepted as follows:

According to the application form “the LB will implement a tender procedure for selection of an external contractor for the delivery of all needed materials for clay modeling which will be used in the training, workshops and festivals”, thus, 70 dry pastels at the unit cost set by the evaluators of 14.62 euro.

Thus, the costs related to the 20 dry pastels are accepted: 20 tool sets x 14.62 euro/unit = 292.4 euro.

As regards the unit cost set by the evaluators, the argument provided by the applicant is very unclear and related to the tool sets of instruments for clay modeling.

- Point 10 and 12 - The applicants appeal the proposed reduction of 140.06 euro representing costs for 20 sketchbooks for drawing out of the envisaged a total of 70 and of 183.50 euro, representing the difference of 20 pencils up to 70 pencils proposed  within activity 7 “Training in sculptural technique” –partially accepted

The costs related to the 20 sketchbooks for drawing are accepted: 20 sketchbooks x 7,01 euro/unit = 140.2 euro

The costs related to the 20 pencils is calculated at the unit cost of the 6.13 euro set by the evaluators: 20 pencils x 6.13 euro/unit = 122.6 euro.  A clarification request on this issue was submitted during the evaluation process, but the applicant provided no answer. Also, the applicant has provided no arguments/justifications regarding the cost unit related to pencils within the compliant.

Beneficiary 2

- Point 2 - The applicants appeal the proposed reduction of the amount of 1942.40 euro for designing the common web page and hosting services – accepted

The argument provided by the applicant is justified: the costs of 2000 Euro for designing and the costs of 240 euro for hosting the website for 12 months observes the ceiling set in Annex C. Thus, the cut of 1942.40 euro from the budget is not accepted.

The budget of the application shall include the amount of 1942.40 euro initially reduced during the evaluation process.

Moreover, during the evaluation process 2,000 euro were unjustified reduced related to the same activity – designing of web site. This amount shall be put back into the budget.

- Point 3 - The applicant appeals the reduction of the amount of 18.000,00 euro representing costs for 3 experts within Activity 6 – rejected by the Complaint Panel.

The argument provided by the applicant for complaining the cutting of 18.000,00 euro is not justified. The Applicant’s Guide states very clearly that the applicant must submit 3 offers or an independent opinion on supporting the proposed costs. The applicant has not submitted 3 offers nor an independent opinion. Moreover, a request of clarification on this issue was submitted to the applicant, but no answer was received.

Therefore, the reduction of 18,000 euro for the 3 external experts needed for Activity 6 made during the evaluation process is justified as “no offers were submitted by the Beneficiary considering that the respective service was not included in Annex C”.

- Point 4 - The applicant appeals the proposed reduction of the following amounts envisaged within activity 6 – Elaborating of new tourist route “The path of clay” – rejected by the Complaint Panel:

  - 8,610.00 euro (70 000 km x 8.2 liters/100km x 1.50€ = 8610 €) for travel for 3 external experts and 1 photographer;

  - 2,080.00 euro (52 days x 3 experts and 1 photographer x 10 euro /person) for daily allowances;

  - 12,000.00 euro (50 nights x 3 experts and 1 photographer x 60 euro) for accommodation.

During the evaluation process, a clarification request was submitted to the applicant for justifying the separation of these costs from those related to contracting the 3 external experts. The applicant provided no answer to this request nor a justified explanation within compliant.

Moreover, the costs with travel, accommodation and allowance for the team expert were not foreseen in the application form. They should have been included under the budget category “Travel and Accommodation costs”.

Therefore, the initial cutting of these costs during the evaluation process is considered justified and the applicant request is considered not justified.

- Point 5 – The applicant appeals the proposed reduction of the amount of 936.00 euro, representing the costs for food and accommodation for 3 persons in addition to the 50 participants, envisaged to take part in the 2 workshops within activity 8 – accepted by the Compliant Panel.

Based on the information included in the application form the 3 persons are the volunteer students, and thus the costs related with their accommodation and food are accepted.

Thus, the costs related to accommodation and food for the 3 volunteer students are accepted: 3 persons X 2 days X 78 Euro x 2 workshops = 936 Euro.

Article 2.2. The new budget of the application shall be submitted to the Monitoring Committee for approval and the lead beneficiary shall be informed accordingly on the content of the MC decision.

Article 3. The decision of the Complaint Panel is final, binding to all parties and not subject of any further complaint proceedings within the Programme.

Signed by

Members of the Complaint Panel

Signature

Member 1 – Managing Authority representative, Ministry of Regional Development and Public Administration, Romania

Signature

Member 2 – National Authority representative, Ministry of Regional Administration and Public Works, Bulgaria

Signature

Member 3 – National Authorities Department representative, Ministry of Regional Development and Public Administration, Romania