## Slide 1
INTERREG V-A
Romania-Bulgaria
Rules of Project Implementation
Alexandria, 27.06.2018
www.interregrobg.eu

## Slide 2: ACTIVITIES
Shall be performed as described within the approved application form. Any modification notification or addendum.
Special attention to details of the services / goods / works. Modifications without notifications /addenda may result in ineligibility of expenditures or might not contribute to the indicators.
Examples
Shall be performed within the timeframe of the approved application form. Any modification reported as being late within the partner report or notification / addendum (in case of major modifications of the timeframe).

## Slide 3: INDICATORS – 1 -
result-orientation of the ESI Funds for 2014 – 2020 period / selected projects with one or more output indicators and one or more result indicators.
Output indicators
Result indicators
Will be reported within the partner / project reports. Final project report, beneficiaries must state if they have fully achieved the contribution to Programme result indicator, as envisaged in the project. Monitoring sources are mandatory (information must be supported by verifiable data).

## Slide 4: INDICATORS – 2 -
Attention!
In case of partial achievement of the indicators at Programme level, the MA may decide to apply financial penalties to the projects, which have not reached their indicators, proportionally with their budgets and the degree of achievement of indicators.
For third call for project, the MA is entitled to decommit project funds by reducing the original project budget and the corresponding ERDF contribution (in case the project contribution to indicators < compared to the application form), as follows:
1. 10% in case the project indicators < 75% of the initial project indicators;
2. 25% in case the project indicators < 50% of the initial project indicators;
3. 10% in case the project did not contribute to the result indicators (a non-quantifiable one).
The moment when the abovementioned is judged is represented by the deadline of achieving the indicators, as mentioned in the Application Form/the deadlines mentioned in the European Commission guidance for closure (not published yet for the current period).

## Slide 5: Investment projects – 1 -
Must submit to JS technical projects / designs for the investments within 10 working days of the design acceptance in its final version + one statement mentioning:
“there are no modifications as compared with the documents within the approved application form (feasibility study /preliminary design)”
or
- “there are modifications which shall be presented in detail and with proper justifications”.
In case of modifications notification / addendum

## Slide 6: Investment projects – 2 -
For all project for which the authorities for environment protection issued the decisions for the registration step (decizia etapei de încadrare) or the environment agreement (acordul de mediu) after 16th of May 2017, the holders of these decisions have the obligation of submitting to the competent environment institutions the notification foreseen by art. 15, para. (2), letter a) of GEO nr. 195/2005 regarding the environment protection.
All environment decisions issued after 16th of May 2017 for EU financed projects must be updated / revised in order to observe the EU directive 2014/52/UE

## Slide 7: REPORTING - ACTIVITIES
Regulation: subsidy contract, art. 6, para. 11; art.7, LB 5; art. 14, alin. 4, lit. f and PIM, chapter 15
Responsible: Lead Beneficiary prepares technical project report, consolidating the information on activities included in the Partner reports submitted to FLC for the respective reporting period or to request a partner report with only information regarding the progress of activities (with 0 expenditure requested) directly submitted to LB, for the part of the reporting period that is not covered by a partner report submitted to FLC.
WHEN?
PIM provision / MA Instruction no. 5
(after the end of the each reporting period, but not later than 10 working days)
HOW?
eMS system / Guidelines for beneficiaries
Content: detailed description of what has been done within the project, by who, where, what results/objectives/indicators were achieved, what resources were used, what problems were met and comparing the achievements with project activities and activities timing with the initial schedule, etc.)

## Slide 8: REPORTING - ACTIVITIES
Final report:
When?
PIM provision, chapter 20 (within 5 months since the end of the implementation period)
How?
Compiling data for the entire project implementation period, is submitted in hard copy (on paper) using the template provided by Annex 19.1 – Final Report (2 original copies and has to be signed by the legal representative of the LB.
Attention!
The final claim for reimbursement must be submitted together with the final report, irrespective of the amount. If not, it will not be processed and, therefore, paid until the final report is also submitted and verified.
For project with training sessions, a list with all participants to the trainings shall be submitted together with the final report (name of the participants, certification /diploma that has been obtained, subject / specialization / other information.

## Slide 9: HORIZONTAL PRINCIPLES
Must contribute to the principles
1. Equal opportunities and non-discrimination
2. Equality between men and women
3. Sustainable development (environment)
Shall be reflected in project activities, outputs and results. See PIM chapter 11.
Final report shall have attached PIM Annex 19.2 - Equal opportunities and non-discrimination questionnaire and Annex 19.3 - Questionnaire on environmental protection

## Slide 10: PROCUREMENTS
All beneficiaries must observe the national legislation regarding the procurements.
Romanian beneficiaries that do not have the status of contracting authorities under the provisions of Law 98/2016 will apply the provisions of Annex 4 of the subsidy contract: “Rules for the assignment of works, supplies and services contract for the Romanian beneficiaries that do not have status of contracting authorities under the provisions of Law 98/2016”, as it was modified by the MA instruction no. 2/2016 (based on the provisions of Order of the Minister of European Fund no. 1284/2016).
Rules for publishing are available at:
http://www.interregrobg.eu/images/fisiere/achizitii/norme-de-aplicare-beneficiari-ro.pdf for Romanian beneficiaries
Specific instructions are set within the PIM related to avoiding conflict of interest in relation with the procurements (section B – Fraud and antifraud measures, chapter 18 – Irregularities and antifraud measures).

## Slide 11: THANK YOU!