## Slide 1
Technical meeting
Contract modifications
Alexandria, 27th of June 2018
www.interregrobg.eu

## Slide 2: Contract modifications
  Considering that the initial Application Form has been evaluated and selected by the Monitoring Committee it is strongly advised that partners limit the number of changes of a project.
  Changes are classified in two categories:
  ● Changes which do not require the signing of an addendum to the subsidy contract – Notifications (Subsidy contract art. 13 para. 7)
  ● Changes which require the signing of an addendum to the subsidy contract (Subsidy contract art. 13 para. 4)

## Slide 3: Contract modifications
  Notifications
  Minor changes which do not alter in a significant way the approved Application Form may be performed by means of a notification.
  The JS will analyse the request in order to verify if it does not fall under one of the cases for which an addendum to the subsidy contract needs to be signed.
  Examples: contact data change, change of the Euro bank account of the LB, modification of the name of the beneficiary (without changing the identification number of the institution), minor changes in the application form, material errors in the text of the contract, etc.

## Slide 4: Contract modifications
  Addenda
  Changes which have a major impact on the approved Application Form shall require the signing of addendum to the contract.
  Beneficiaries should try to limit these changes as much as possible, as they usually alter the initial financing conditions.
  Depending on their type, they can be approved either by the Managing Authority or by the Monitoring Committee.
  Examples: changes in the project partner organizations, changes in the partnership, reallocation of funds between budgetary chapters (only in exceptional and duly justified cases), major changes in the Application Form, etc.

## Slide 5: Contract modifications
  A request for modification should be submitted to the JS with minimum 30 days before they intend to produce effects.
  The last request for modification should be submitted no later than 2 months before the end date of the implementation period.
  The requests for modification have to be submitted by the LB to the JS. Therefore, take also into consideration the time necessary for the LB to compile the requests for modification received from the project partners.

## Slide 6: Contract modifications
  All addenda and notifications will be requested by the Lead Beneficiaries to the JS in hard copy (written form) and only after the approval on paper the documents related to the approved contract amendment will be uploaded in the e-MS by the Lead Beneficiary in maximum 3 working days in section “Attachment”.
  All related modifications will be operated in the system by the Lead Beneficiary (through “Modification Request”) in maximum 3 working days after the approval on paper.
  In case beneficiaries have a Partner/Project Report in progress in the system and the approved contract modifications have no impact on the reporting for the current reporting period, the LB may ask the JS the extension of the deadline.